## Task Monitor
GROUP 2 — TASK MONITOR
Project Manager: Blamen ¦ System: GSO Gateway (ManageIT) ¦ JRMSU
STATUS: 🔄 In Progress ¦ ✅ Done ¦ ❌ Blocked
# | Task | Details | Assigned To | Status
🎨 FRONTEND
FE1 | Make notifications clickable | When a user clicks a notification it should open the related content — request details, schedule, or feedback page. | Frenzy | ✅ Done
FE2 | Design request approval interface for Head, Staff, and Campus Director | Create a UI where Head, Staff, and Campus Director can approve or deny requests. Must include a remarks/reason input field for denial. | Frenzy | ✅ Done
FE3 | Update the request design for Staff, Head, and Campus Director | Redesign the request view page for Staff, Head, and Campus Director — show request details clearly with action buttons (Approve, Deny, Verify, Mark Done). | Frenzy | ✅ Done
FE4 | Display feedback message when request is rejected | Show the rejection reason/remarks to the requester when their request is denied by the Head. | Frenzy
⚙️ BACKEND
BE1 | Implement notification redirect system | Add link and reference_id to notifications table so clicking a notification opens the related content. | Mc Laurence
BE2 | Fix request approve/disapprove functionality | Fix the bug in Head and Staff approval — status must update correctly and notify the next role. | Mc Laurence
BE3 | Add admin feedback system when rejecting requests | Require remarks field when Head denies a request — store in DB and display to the requester. | Mc Laurence
BE4 | Update approve icon after feedback submission | Change the approve button icon state after Head submits approval or denial so no double-approval happens. | Mc Laurence
BE5 | Implement priority scheduling after Campus Director approval | Auto-assign priority number and update status to In Progress after Campus Director gives final approval. | Mc Laurence
BE6 | Implement feedback after service system | After Staff marks request as Done, allow Requester to submit feedback using sqd0–sqd8 satisfaction ratings. | Mc Laurence
BE7 | Allow Head to add services | Create an API endpoint accessible only by Head role to add new maintenance service types to the system. | Mc Laurence
BE8 | Implement request status viewing for users | Requesters can track their request through all status stages: Submitted → Verified → Approved → Done. | Mc Laurence
BE9 | Track pending accounts and pending schedules | Admin sees list of all pending user accounts not yet approved. Head sees all pending schedule requests. | Mc Laurence
BE10 | Fix schedule/calendar display for Head, Staff, and Requester | Each role sees their relevant schedule — fix role-based calendar visibility and data retrieval. | Mc Laurence